## Cover
Company | Agile Lab Pte Ltd
Department
Document Title | ISMS Internal Audit
Standard(s) | ISO27001 Information technology ‒ Security Techniques ‒ Information security management systems ‒ Requirements
Applicable clauses | 9.2
Last review | 2020-12-11 | Classification | Confidential
Prepared by | Lim Sek Seong & Daniel Lim | Date | 2020-12-12
Approved by |  | Date | 2020-12-16

## Attendance
No. | Name | Department / Function | Location

## ISO27001 clauses
Clause | Clause Title | Audit finding | Evidence/Observation | Corrective Actions | Improvement Areas
4 | Context of the organization
4.1 | Understanding the organization and its context | Comply
4.2 | Understanding the needs and expectations of interested parties | Comply
4.3 | Determining the scope of the information security management system | Comply
4.4 | Information security management system | Comply
5 | Leadership
5.1 | Leadership and Commitment | Comply
5.2 | Policy | Comply
5.3 | Organization, roles, responsibilities and authorities | Comply
6 | Planning
6.1 | Action to address Risk and Opportunities
6.1.1 | General | Comply
6.1.2 | Information security risk assessment | Comply
6.1.3 | Information security risk treatment | Comply
6.2 | Information security objectives and planning to achieve them | Comply
7 | Support
7.1 | Resources | Comply
7.2 | Competence | Comply
7.3 | Awareness | Comply
7.4 | Communication | Comply
7.5 | Documented information
7.5.1 | General | Comply
7.5.2 | Creating & updating | Comply
7.5.3 | Control of documented information | Comply
8 | Operation
8.1 | Operational planning & control | Comply
8.2 | Information security risk assessment | Comply
8.3 | Information security risk treatment | Comply
9 | Performance evaluation
9.1 | Monitoring, measurement, analysis and evaluation | Comply
9.2 | Internal audit | Comply
9.3 | Management review | Comply
10 | Improvement
10.1 | Nonconfirminty & corrective action | Comply
10.2 | Continual improvement | Comply

## Controls-Objectives
ID | Controls according to ISO/IEC 27001 | Controls | Audit Rating | Remarks | Corrective Actions | Improvement Areas | Client's Response
A.5 | Information security policies
A.5.1 | Management direction for information security | Objective: To provide management direction and support for information security in accordance with business requirements and relevant laws and regulations
A.5.1.1 | Policies for information security | A set of policies for information security shall be defined, approved by management, published and communicated to employees and relevant external parties. | Comply
A.5.1.2 | Review of the policies for information security | The policies for information security shall be reviewed at planned intervals or if significant changes occur to ensure their continuing suitability, adequacy and effectiveness. | Comply
A.6 | Organization of information security
A.6.1 | Internal organization | Objective: To establish a management framework to initiate and control the implementation and operation of information security within the organization.
A.6.1.1 | Information security roles and responsibilities | All information security responsibilities shall be defined and allocated. | Comply
A.6.1.2 | Segregation of duties | Conflicting duties and areas of responsibility shall be segregated to reduce opportunities for unauthorized or unintentional modification or misuse of the organization's assets. | Comply
A.6.1.3 | Contact with authorities | Appropriate contacts with relevant authorities shall be maintained. | Comply
A.6.1.4 | Contact with special interest groups | Appropriate contacts with special interest groups or other specialist security forums and professional associations shall be maintained. | Comply
A.6.1.5 | Information security in project management | Information security shall be addressed in project management, regardless of the type of project. | Comply
A.6.2 | Mobile devices and teleworking | Objective: To ensure the security of teleworking and use of mobile devices.
A.6.2.1 | Mobile device policy | A policy and supporting security measures shall be adopted to manage the risks introduced by using mobile devices. | Comply
A.6.2.2 | Teleworking | A policy and supporting security measures shall be implemented to protect information accessed, processed or stored at teleworking sites. | Comply
A.7 | Human resource security
A.7.1 | Prior to employment | Objective: To ensure that employees and contractors understand their responsibilities and are suitable for the roles for which they are considered.
A.7.1.1 | Screening | Background verification checks on all candidates for employment shall be carried out in accordance with relevant laws, regulations and ethics, and shall be proportional to the business requirements, the classification of the information to accessed and the perceived risks. | Comply
A.7.1.2 | Terms and conditions of employment | The contractual agreements with employees and contractors shall state their and the organization's responsibilities for information security. | Comply
A.7.2 | During employment | Objective: To ensure that employees and contractors are aware of and fulfil their information security responsibilities.
A.7.2.1 | Management responsibilities | Management shall require all employees and contractors to apply information security in accordance with the established policies and procedures for the organization. | Comply
A.7.2.2 | Information security awareness, education and training | All employees of the organization and, where relevant, contractors shall receive appropriate awareness education and training, and regular updates in the organizational policies and procedures, as relevant for their job function. | Comply
A.7.2.3 | Disciplinary process | There shall be a formal and communicated disciplinary process in place to take action against employees who have committed an information security breach. | Comply
A.7.3 | Termination and change of employment | Objective: To protect the organization's interests as part of the process of changing or terminating employment.
A.7.3.1 | Termination or change of employment responsibilities | Information security responsibilities and duties that remain valid after termination or change of employment shall be defined and communicated to the employee or contractor, and enforced. | Comply
A.8 | Asset management
A.8.1 | Responsibility for assets | Objective: To identify organizational assets and define appropriate protection responsibilities.
A.8.1.1 | Inventory of assets | Assets associated with information and information processing facilities shall be identified and an inventory of these assets shall be drawn up and maintained. | Comply
A.8.1.2 | Ownership of assets | Assets maintained in the inventory shall be owned. | Comply
A.8.1.3 | Acceptable use of assets | Rules for the acceptable use of information and of assets associated with the information and information processing facilities shall be identified, documented and implemented. | Comply
A.8.1.4 | Return of assets | All employees and external party users shall return all of the organizational assets in their possession upon termination of their employment, contract or agreement. | Comply
A.8.2 | Information classification | Objective: To ensure that information receives an appropriate level of protection in accordance with its importance to the organization.
A.8.2.1 | Classification of information | Information shall be classified in terms of legal requirements, value, criticality and sensitivity to unauthorized disclosure or modification. | Comply
A.8.2.2 | Labelling of information | An appropriate set of procedures for information labelling shall be developed and implemented in accordance with the information classification scheme adopted by the organization. | Comply
A.8.2.3 | Handling of assets | Procedures for handling assets shall be developed and implemented in accordance with the information classification scheme adopted by the organization. | Comply
A.8.3 | Media handling | Objective: To prevent unauthorized disclosure, modification, removal or destruction of information stored on media.
A.8.3.1 | Management of removable media | Procedures shall be implemented for the management of removable media in accordance with the classification scheme adopted by the organization. | Comply
A.8.3.2 | Disposal of media | Media shall be disposed of securely when no longer required, using formal procedures. | Comply
A.8.3.3 | Physical media transfer | Media containing information shall be protected against unauthorized access, misuse or corruption during transportation. | Comply
A.9 | Access control
A.9.1 | Business requirements of access control | Objective: To limit access to information and processing facilities.
A.9.1.1 | Access control policy | An access control policy shall be established, documented and reviewed based on business and information security requirements. | Comply
A.9.1.2 | Access to networks and network services | Users shall only be provided with access to the network and network services that they have been specifically authorized to use. | Comply
A.9.2 | User access management | Objective: To ensure authorized user access and to prevent unauthorized user access to systems and services.
A.9.2.1 | User registration and de-registration | A formal user registration and de-registration process shall be implemented to enable assignment of access rights. | Comply
A.9.2.2 | User access provisioning | A formal user access provisioning process shall be implemented to assign or revoke access rights for all user types to all systems and services. | Comply
A.9.2.3 | Management of privileged access rights | The allocation and use of privileges access rights shall be restricted and controlled. | Comply
A.9.2.4 | Management of secret authentication information of users | The allocation of secret authentication information shall be controlled through a formal management process. | Comply
A.9.2.5 | Review of user access rights | Asset owners shall review users' access rights at regular intervals. | Comply
A.9.2.6 | Removal or adjustment of access rights | The access rights of all employees and external party users to information and information processing facilities shall be removed upon termination of their employment, contract or agreement, or adjusted upon change. | Comply
A.9.3 | User responsibilities | Objective: To make users accountable for safeguarding their authentication information.
A.9.3.1 | Use of secret authentication information | Users shall be required to follow the organization's practices in the use of secret authentication information. | Comply
A.9.4 | System and application access control | Objective: To prevent unauthorized access to systems and applications.
A.9.4.1 | Information access restriction | Access to information and application system functions shall be restricted in accordance with the access control policy. | Comply
A.9.4.2 | Secure log-on procedures | Where required by the access control policy, access to systems and applications shall be controlled by a secure log-on procedure. | Comply
A.9.4.3 | Password management system | Password management systems shall be interactive and shall ensure quality passwords. | Comply
A.9.4.4 | Use of privileged utility programs | The use of utility programs that might be capable of overriding system and application controls shall be restricted and tightly controlled. | Comply
A.9.4.5 | Access control to program source code | Access to program source code shall be restricted. | Comply
A.10 | Cryptography
A.10.1 | Cryptographic controls | Objective: To ensure proper and effective use of cryptography to protect the confidentiality, authenticity and/or integrity of information.
A.10.1.1 | Policy on the use of cryptographic controls | A policy on the use of cryptographic controls for protection of information shall be developed and implemented. | Comply
A.10.1.2 | Key management | A policy on the use, protection and lifetime of cryptographic keys shall be developed and implemented through the whole lifecycle. | Comply
A.11 | Physical and environmental security
A.11.1 | Secure areas | Objective: To prevent unauthorized physical access, damage and interference to the organization's information and information processing facilities.
A.11.1.1 | Physical security perimeter | Security perimeters shall be defined and used to protect areas that contain either sensitive or critical information and information processing facilities. | Comply
A.11.1.2 | Physical entry controls | Secure areas shall be protected by appropriate entry controls to ensure that only authorized personnel are allowed access. | Comply
A.11.1.3 | Securing offices, rooms and facilities | Physical security for offices, rooms and facilities shall be designed and applied. | Comply
A.11.1.4 | Protecting against external and environmental threats | Physical protection against natural disasters, malicious attack or accidents shall be designed and applied. | Comply
A.11.1.5 | Working in secure areas | Procedures for working in secure areas shall be designed and applied. | Comply
A.11.1.6 | Delivery and loading areas | Access points such as delivery and loading areas, and other points where unauthorized persons could enter the premises shall be controlled and, if possible, isolated from information processing facilities to avoid unauthorized access. | Comply
A.11.2 | Equipment | Objective: To prevent loss, damage, theft or compromise of assets and interruption to the organization's operations.
A.11.2.1 | Equipment siting and protection | Equipment shall be sited and protected to reduce the risks from environmental threats and hazards, and opportunities for unauthorized access. | Comply
A.11.2.2 | Supporting utilities | Equipment shall be protected from power failures and other disruptions caused by failures in supporting utilities. | Comply
A.11.2.3 | Cabling security | Power and telecommunications cabling carrying data or supporting information services shall be protected from interception, interference or damage. | Comply
A.11.2.4 | Equipment maintenance | Equipment shall be correctly maintained to ensure its continued availability and integrity. | Comply
A.11.2.5 | Removal of assets | Equipment, information or software shall not be taken off-site without prior authorization. | Comply
A.11.2.6 | Security of equipment and assets off-premises | Security shall be applied to off-site assets taking into account the different risks or working outside the organization's premises. | Comply
A.11.2.7 | Secure disposal or reuse of equipment | All items of equipment containing storage media shall be verified to ensure that any sensitive data and licensed software has been removed or securely overwritten prior to disposal or re-use. | Comply
A.11.2.8 | Unattended user equipment | Users shall ensure that unattended equipment has appropriate protection. | Comply
A.11.2.9 | Clear desk and clear screen policy | A clear desk policy for papers and removable storage media and a clear screen policy for information processing facilities shall be adopted. | Comply
A.12 | Operations security
A.12.1 | Operational procedures and responsibilities | Objective: To ensure correct and secure operations of information processing facilities.
A.12.1.1 | Documented operating procedures | Operating procedures shall be documented and made available to users who need them. | Comply
A.12.1.2 | Change management | Changes to the organization, business processes, information processing facilities and systems that affect information security shall be controlled. | Comply
A.12.1.3 | Capacity management | The use of resources shall be monitored, tuned and projections made of future capacity requirements to ensure the required system performance. | Comply
A.12.1.4 | Separation of development, testing and operational environments | Development, testing, and operational environments shall be separated to reduce the risks of unauthorized access or changes to the operational environment. | Comply
A.12.2 | Protection from malware | Objective: To ensure that information and information processing facilities are protected against malware.
A.12.2.1 | Controls against malware | Detection, prevention and recovery controls to protect against malware shall be implemented, combined with appropriate user awareness. | Comply
A.12.3 | Backup | Objective: To protect against data loss.
A.12.3.1 | Information backup | Backup copies of information, software and system images shall be taken and tested regularly in accordance with an agreed backup policy. | Comply
A.12.4 | Logging and monitoring | Objective: To record events and generate evidence.
A.12.4.1 | Event logging | Event logs recording user activities, exceptions, faults and information security events shall be produced, kept and regularly reviewed. | Comply
A.12.4.2 | Protection of log information | Logging facilities and log information shall be protected against tampering and unauthorized access. | Comply
A.12.4.3 | Administrator and operator logs | System administrator and system operation activities shall be logged and the logs protected and regularly reviewed. | Comply
A.12.4.4 | Clock synchronization | The clocks of all relevant information processing systems within an organization or security domain shall be synchronized to a single reference time source. | Comply
A.12.5 | Control of operational software | Objective: To ensure integrity of operational systems.
A.12.5.1 | Installation of software on operational systems | Procedures shall be implemented to control the installation of software on operational systems. | Comply
A.12.6 | Technical vulnerability management | Objective: To prevent exploitation of technical vulnerabilities.
A.12.6.1 | Management of technical vulnerabilities | Information about technical vulnerabilities of information systems being used shall be obtained in a timely fashion, the organization's exposure to such vulnerabilities evaluated and appropriate measures taken to address the associated risks. | Comply
A.12.6.2 | Restrictions on software installation | Rules governing the installation of software by users shall be established and implemented. | Comply
A.12.7 | Information systems audit considerations | Objective: To minimize the impact of audit activities on operational systems.
A.12.7.1 | Information systems audit controls | Audit requirements and activities involving verification of operational systems shall be carefully planned and agreed to minimize disruptions to business processes. | Comply
A.13 | Communications security
A.13.1 | Network security management | Objective: To ensure the protection of information in networks and its supporting information processing facilities.
A.13.1.1 | Network controls | Networks shall be managed and controlled to protect information in systems and applications. | Comply
A.13.1.2 | Security of network services | Security mechanisms, service levels and management requirements of all network services shall be identified and included in network services agreements, whether these services are provided in-house or outsourced. | Comply
A.13.1.3 | Segregation in networks | Groups of information services, users and information systems shall be segregated on networks. | Comply
A.13.2 | Information transfer | Objective: To maintain the security of information transferred within an organization and with any external entity.
A.13.2.1 | Information transfer policies and procedures | Transfer of information through the use of communications devices and systems need to be protected. | Comply
A.13.2.2 | Agreements on information transfer | The secure transfer of critical business information (like data files) between the organization and external parties are discussed and agreed. | Comply
A.13.2.3 | Electronic messaging | Information transferred through electronic messaging is appropriately protected. | Comply
A.13.2.4 | Confidentiality or nondisclosure agreements | Requirements for confidentiality or non-disclosure agreements reflecting the organization's needs for the protection of information shall be identified, regularly reviewed and documented. | Comply
A.14 | System acquisition, development and maintenance
A.14.1 | Security requirements of information systems | Objective: To ensure that information security is an integral part of information systems across the entire lifecycle. This also includes the requirements for information system which provides services over public networks.
A.14.1.1 | Information security requirements analysis and specification | The information security related requirements shall be included in the requirements for new information systems or enhancements to existing information systems. | Comply
A.14.1.2 | Securing application services on public networks | Information involve in application services passing over public networks shall be protected from fraudulent activity, contract dispute and unauthorized disclosure and modification. | Comply
A.14.1.3 | Protecting application services transactions | Information involved in application service transactions shall be protected to prevent incomplete transmission, mis-routing, unauthorized message alteration, unauthorized disclosure, unauthorized message duplication or replay. | Comply
A.14.2 | Security in development and support processes | Objective: To ensure that information security is designed and implemented within the development lifecycle of information systems.
A.14.2.1 | Secure development policy | Rules for the development of software and systems shall be established and applied to developments within the organization. | Comply
A.14.2.2 | System change control procedures | Changes to systems within the development of the lifecycle shall be controlled by the use of formal change control procedures. | Comply
A.14.2.3 | Technical review of applications after operating platform changes | When operating platforms are changed, business critical applications shall be reviewed and tested to ensure there is no adverse impact on organizational operations or security. | Comply
A.14.2.4 | Restrictions on changes to software packages | Modifications to software packages shall be discouraged, limited to necessary changes and all changes shall be strictly controlled. | Comply
A.14.2.5 | Secure system engineering principles | Principles for engineering secure systems shall be established, documented, maintained and applied to any information system implementation efforts. | Comply
A.14.2.6 | Secure development environment | Organizations shall establish and appropriately protect secure development environments for system development and integration efforts that cover the entire system development lifecycle. | Comply
A.14.2.7 | Outsourced development | The organization shall supervise and monitor the activity of outsourced system development. | Comply
A.14.2.8 | System security testing | Testing of security functionality shall be carried out during development. | Comply
A.14.2.9 | System acceptance testing | Acceptance of testing programs and related criteria shall be established for new information systems, upgrades and new versions. | Comply
A.14.3 | Test data | Objective: To ensure the protection of data used for testing.
A.14.3.1 | Protection of test data | Test data shall be selected carefully, protected and controlled. | Comply
A.15 | Supplier relationships
A.15.1 | Information security in supplier relationships | Objective: To ensure the protection of the organization's assets that is accessible by suppliers.
A.15.1.1 | Information security policy for supplier relationships | Information security requirements for mitigating the risks associated with suppliers' access to the organization's assets shall be agreed with the supplier and documented. | Comply
A.15.1.2 | Addressing security within supplier agreements | All relevant information security requirements shall be established and agreed with each supplier that may access, process, store, communicated or provide IT infrastructure components for the organization's information. | Comply
A.15.1.3 | Information and communication technology supply chain | Agreements with suppliers shall include requirement to address the information security risks associated with information and communications technology services and product supply chain. | Comply
A.15.2 | Supplier service delivery management | Objective: To maintain an agreed level of information security and service delivery in line with supplier agreements.
A.15.2.1 | Monitoring and review of supplier services | Organizations shall regularly monitor, review and audit supplier service delivery. | Comply
A.15.2.2 | Managing changes to supplier services | Changes to the provision of services by suppliers, including maintaining and improving existing information security policies, procedures and control shall be managed, taking into account the criticality of business information, systems and processes involved and re-assessment of risks. | Comply
A.16 | Information security incident management
A.16.1 | Management of information security incidents and improvements | Objective: To ensure a consistent and effective approach to the management of information security incidents, including communication on security events and weaknesses.
A.16.1.1 | Responsibilities and procedures | Management responsibilities and procedures shall be established to ensure a quick, effective and orderly response to information security incidents. | Comply
A.16.1.2 | Reporting information security events | Information security events shall be reported through appropriate management channels as quickly as possible. | Comply
A.16.1.3 | Reporting information security weaknesses | Employees and contractors using the organization's information systems and services shall be required to note and report an observed or suspected information security weaknesses in systems or services | Comply
A.16.1.4 | Assessment of and decision on information security events security incidents | Information security events shall be assessed and it shall be decided if they are to be classified as information security incidents. | Comply
A.16.1.5 | Response to information security incidents | Information security incidents shall be responded to in accordance with the documented procedures. | Comply
A.16.1.6 | Response to information security incidents | Knowledge gained form analysing and resolving information security incident shall be used to reduce the likelihood or impact of future incidents. | Comply
A.16.1.7 | Response to information security incidents | The organization shall define and apply procedures for the identification, collection, acquisition and preservation of information, which can serve as evidence. | Comply
A.17 | Information security aspects of business continuity management
A.17.1 | Information security continuity | Objective: Information security continuity shall be embedded in the organization's business continuity management system.
A.17.1.1 | Planning information security continuity | The organization shall determine its requirements for information security and the continuity of information security management in adverse situations, e.g. during a crisis or disaster. | Comply
A.17.1.2 | Implementing information security continuity | The organization shall establish, document, implement and maintain processes, procedures and controls to ensure the required level of continuity for information security during an adverse situation. | Comply
A.17.1.3 | Verify, review and evaluate information security continuity | The organization shall verify the established and implemented information security continuity controls at regular intervals in order to ensure that they are valid and effective during adverse situations. | Comply
A.17.2 | Redundancies | Objective: To ensure availability of information processing facilities.
A.17.2.1 | Availability of information processing facilities | Information processing facilities shall be implemented with redundancy sufficient to meet availability requirements. | Comply
A.18 | Compliance
A.18.1 | Compliance with legal and contractual requirements | Objective: To avoid breaches of legal, statutory, regulatory or contractual obligations related to information security and of any security requirements.
A.18.1.1 | Identification of applicable legislation and contractual requirements | All relevant legislative statutory, regulatory, contractual requirements and the organization's approach to meet these requirements shall be explicitly identified, documented and kept up to date for each information system and the organization. | Comply
A.18.1.2 | Intellectual property rights | Appropriate procedures shall be implemented to ensure compliance with legislative, regulatory and contractual requirements related to intellectual property rights and use of proprietary software products. | Comply
A.18.1.3 | Protection of records | Records shall be protected from loss, destruction , falsification, unauthorized access and unauthorized release, in accordance with legislator, regulatory, contractual and business requirements. | Comply
A.18.1.4 | Privacy and protection of personally identifiable information | Privacy and protection of personally identifiable information shall be ensured as required in relevant legislation and regulation where applicable. | Comply
A.18.1.5 | Regulation of cryptographic controls | Cryptographic controls shall be used compliance with all relevant agreements, legislation and regulations. | Comply
A.18.2 | Information security reviews | Objective: To ensure that information security is implemented and operated in accordance with the organizational policies and procedures.
A.18.2.1 | Independent review of information security | The organization's approach to managing information security and its implementation (i.e. control objectives, controls, policies, processes and procedures for information security) shall be reviewed independently at planned intervals or when significant changes occur. | Comply
A.18.2.2 | Compliance with security policies and standards | Managers shall regularly review the compliance of information processing and procedures within their area of responsibility with the appropriate security policies, standards and any other security requirements. | Comply
A.18.2.3 | Technical compliance review | Information systems shall be regularly reviewed for compliance with the organization's information security policies and standards. | Comply

## 27001-IAQ
Clause | Requirement of the standard | Audit finding | Evidence
4.2 | Did the organization determine interested parties?
4.2 | Does the list of all of interested parties’ requirements exist?
4.3 | Is the scope documented with clearly defined boundaries and interfaces?
5.1 | Are the general ISMS objectives compatible with the strategic direction?
5.1 | How does the management ensure that ISMS achieves its objectives?
5.2 | Does Information Security Policy exist with objectives or framework for setting objectives?
5.2 | Is Information Security Policy communicated within the company?
5.3 | Are roles and responsibilities for information security assigned and communicated?
6.1.2 | Is the risk assessment process documented, including the risk acceptance criteria and criteria for risk assessment?
6.1.2, 8.2 | Are the risks identified, their owners, likelihood, consequences, and the level of risk; are these results documented?
6.1.3 | Is the risk treatment process documented, including the risk treatment options?
6.1.3, 8.3 | Are all the unacceptable risks treated using the options and controls from Annex A; are these results documented?
6.1.3 | Is Statement of Applicability produced with justifications and status for each control?
6.1.3, 8.3 | Does Risk treatment plan exist, approved by risk owners?
6.2 | Does Risk treatment plan define who is responsible for implementation of which control, with which resources, what are the deadlines, and what is the evaluation method?
7.1 | Are adequate resources provided for all the elements of ISMS?
7.2 | Are required competences defined, trainings performed, and records of competences maintained?
7.3 | Is the personnel aware of Information security policy, of their role, and consequences of not complying with the rules?
7.4 | Does the process for communication related to information security exist, including the responsibilities and what to communicate?
7.5 | Does the process for managing documents and records exist, including who reviews and approves documents, where and how they are published, stored and protected?
7.5 | Are documents of external origin controlled?
8.1 | Are outsourced processes identified and controlled?
9.1 | Is it defined what needs to be measured, by which method, who is responsible, who will analyse and evaluate the results?
9.1 | Are the results of measurement documented and reported to responsible persons?
9.2 | Does an audit program exist that defines the timing, responsibilities, reporting, audit criteria and scope?
9.2 | Are internal audits performed according to audit program, results reported through the Internal audit report and relevant corrective actions raised?
9.3 | Is management review regularly performed, and are the results documented in minutes of the meeting?
9.3 | Did management decide on all the crucial issues important for the success of the ISMS?
10.1 | Does the organization react to every nonconformity?
10.1 | Does the organization consider eliminating the cause of nonconformity and, where appropriate, take corrective action?
10.1 | Are all nonconformities recorded, together with corrective actions?
A.5.1.1 | Are all necessary information security policies approved by management and published?
A.5.1.2 | Are all information security policies reviewed and updated?
A.6.1.1 | Are all information security responsibilities clearly defined through one or several documents?
A.6.1.2 | Are duties and responsibilities defined in such a way to avoid conflict of interest, particularly with the information and systems where high risks are involved?
A.6.1.3 | Is it clearly defined who should be in contact with which authorities?
A.6.1.4 | Is it clearly defined who should be in contact with special interest groups or professional associations?
A.6.1.5 | Are information security rules included in every project?
A.6.2.1 | Are there rules for secure handling of mobile devices?
A.6.2.2 | Are there rules defining how the company information is protected at teleworking sites?
A.7.1.1 | Are background checks performed on candidates for employment or for contractors?
A.7.1.2 | Do the agreements with employees and contractors specify the information security responsibilities?
A.7.2.1 | Is management actively requiring all employees and contractors to comply with information security rules?
A.7.2.2 | Are all relevant employees and contractors being trained to perform their security duties, and do the awareness programs exist?
A.7.2.3 | Have all employees who have committed a security breach been subject to a formal disciplinary process?
A.7.3.1 | Are information security responsibilities that remain valid after the termination of employment defined in the agreement?
A.8.1.1 | Is an Inventory of assets drawn up?
A.8.1.2 | Does every asset in Inventory of assets have a designated owner?
A.8.1.3 | Are the rules for appropriate handling of information and assets documented?
A.8.1.4 | Did all the employees and contractors return all the company assets when their employment was terminated?
A.8.2.1 | Is the information classified according to specified criteria?
A.8.2.2 | Is the classified information labelled according to the defined procedures?
A.8.2.3 | Are there procedures which define how to handle classified information?
A.8.3.1 | Are there the procedures which define how to handle removable media in line with the classification rules?
A.8.3.2 | Are there formal procedures for disposing of the media?
A.8.3.3 | Is the media that contains sensitive information protected during transportation?
A.9.1.1 | Is there an Access control policy which defines business and security requirements for access control?
A.9.1.2 | Do the users have access only to those networks and services they are specifically authorized for?
A.9.2.1 | Are access rights provided via a formal registration process?
A.9.2.2 | Is there a formal access control system when logging into information systems?
A.9.2.3 | Are privileged access rights managed with special care?
A.9.2.4 | Are initial passwords and other secret authentication information provided in a secure way?
A.9.2.5 | Do asset owners periodically check all the privileged access rights?
A.9.2.6 | Have the access rights to all employees and contractors been removed upon the termination of their contracts?
A.9.3.1 | Are there clear rules for users on how to protect passwords and other authentication information?
A.9.4.1 | Is the access to databases and applications restricted according to the Access control policy?
A.9.4.2 | Is secure log-on required on systems according to the Access control policy?
A.9.4.3 | Are the systems that manage passwords interactive, and enable the creation of secure passwords?
A.9.4.4 | Is the use of utility tools that can override the security controls of applications and systems strictly controlled and limited to narrow circle of employees?
A.9.4.5 | Is the access to source code restricted to authorized persons?
A.10.1.1 | Does the policy that regulates encryption and other cryptographic controls exist?
A.10.1.2 | Are the cryptographic keys properly protected?
A.11.1.1 | Do secure areas that protect sensitive information exist?
A.11.1.2 | Is the entrance to secure areas protected with controls that allow only the authorized persons to enter?
A.11.1.3 | Are secure areas located in such a way that they are not visible to outsiders, and not easily reached from the outside?
A.11.1.4 | Are the alarms, fire-protection, and other systems installed?
A.11.1.5 | Are working procedures for secure areas defined and complied with?
A.11.1.6 | Are delivery and loading areas controlled in such a way that unauthorized persons cannot enter the company premises?
A.11.2.1 | Is the equipment sited in such a way to protect it from unauthorized access, and from environmental threats?
A.11.2.2 | Does the equipment have an uninterruptible power supply?
A.11.2.3 | Are the power and telecommunication cables adequately protected?
A.11.2.4 | Is the equipment maintained regularly according to manufacturers’ specifications and good practice?
A.11.2.5 | Is the authorization for information and other assets given each time they are taken out of the company premises?
A.11.2.6 | Are the company assets adequately protected when they are not located at the company premises?
A.11.2.7 | Are all the information and licensed software removed from media or equipment containing media when disposed of?
A.11.2.8 | Are users protecting their equipment when not in physical possession of it?
A.11.2.9 | Is there a policy which forces users to remove papers and media when not present, and lock their screens?
A.12.1.1 | Have the operating procedures for IT processes been documented?
A.12.1.2 | Are all the changes to IT systems, but also to other processes that could affect information security, strictly controlled?
A.12.1.3 | Does someone monitor use of resources and project the required capacity?
A.12.1.4 | Are development, testing and production environments strictly separated?
A.12.2.1 | Are anti-virus software, and other software for malware protection, installed and updated?
A.12.3.1 | Is the backup policy developed; is the backup performed according to this policy?
A.12.4.1 | Are all user logs, faults and other events from IT systems logged, and does someone check them?
A.12.4.2 | Are logs protected in such a way that unauthorized persons cannot change them?
A.12.4.3 | Are administrator logs protected in such a way that system administrators cannot change them or delete them; are they regularly checked?
A.12.4.4 | Are clocks on all IT systems synchronized with a single source of correct time?
A.12.5.1 | Is installation of software strictly controlled; do procedures exist for that purpose?
A.12.6.1 | Is there someone in charge of collecting information about vulnerabilities, and are those vulnerabilities promptly resolved?
A.12.6.2 | Are there specific rules that define restrictions of software installation by users?
A.12.7.1 | Are audits of production systems planned and executed in such a way that they minimize the risk of disruption?
A.13.1.1 | Are the networks controlled in such a way that they protect information in systems and applications?
A.13.1.2 | Are security requirements for in-house and external network services defined, and included in agreements?
A.13.1.3 | Are groups of users, services and systems segregated in different networks?
A.13.2.1 | Is the protection of information transfer regulated in formal policies and procedures?
A.13.2.2 | Do agreements with third parties exist which regulate the security of information transfer?
A.13.2.3 | Are the messages that are exchanged over the networks properly protected?
A.13.2.4 | Did the company list all the confidentiality clauses that need to be included in agreements with third parties?
A.14.1.1 | Are security requirements defined for new information systems, or for any changes to them?
A.14.1.2 | Is the information involved in applications that is transferred through the public networks appropriately protected?
A.14.1.3 | How are information protected in application transaction services?
A.14.2.1 | Are the rules for the secure development of software and systems defined?
A.14.2.2 | Do formal change control procedures exist for making any changes to the new or existing systems?
A.14.2.3 | Are critical applications tested after the operating systems have been changed or updated?
A.14.2.4 | Are only the changes that are really necessary performed to information systems?
A.14.2.5 | Are the principles for engineering secure systems documented and implemented?
A.14.2.6 | Is the development environment appropriately secured from unauthorized access and change?
A.14.2.7 | Is the outsourced development of systems monitored?
A.14.2.8 | Is testing for proper implementation of security requirements performed during the development?
A.14.2.9 | Are the criteria for accepting the systems defined?
A.14.3.1 | Are the test data carefully selected and protected?
A.15.1.1 | Is the policy on how to treat the risks related to suppliers and partners documented?
A.15.1.2 | Are all the relevant security requirements included in the agreements with the suppliers and partners?
A.15.1.3 | Do the agreements with cloud providers and other suppliers include security requirements for ensuring the reliable delivery of services?
A.15.2.1 | Are suppliers regularly monitored for compliance with the security requirements, and audited if appropriate?
A.15.2.2 | When making changes to arrangements and contracts with suppliers and partners, are risks and existing processes taken into account?
A.16.1.1 | Are procedures and responsibilities for managing incidents clearly defined?
A.16.1.2 | Are all information security events reported in a timely manner?
A.16.1.3 | Are employees and contractors reporting on security weaknesses?
A.16.1.4 | Are all security events assessed and classified?
A.16.1.5 | Are procedures on how to respond to incidents documented?
A.16.1.6 | Are security incidents analysed in order to gain knowledge on how to prevent them?
A.16.1.7 | Do procedures exist which define how to collect evidence that will be acceptable during the legal process?
A.17.1.1 | Are requirements for continuity of information security defined?
A.17.1.2 | Do procedures exist that ensure the continuity of information security during a crisis or a disaster?
A.17.1.3 | Is exercising and testing performed in order to ensure effective response?
A.17.2.1 | Does IT infrastructure have redundancy (e.g. secondary location) to fulfil the expectations during disasters?
A.18.1.1 | Are all legislative, regulatory, contractual and other security requirements listed and documented?
A.18.1.2 | Do procedures exist that ensure the enforcement of intellectual property rights, in particular, the used of licensed software?
A.18.1.3 | Are all the records protected according to identified regulatory, contractual and other requirements?
A.18.1.4 | Is personally identifiable information protected as required in laws and regulations?
A.18.1.5 | Are cryptographic controls used as required in laws and regulations?
A.18.2.1 | Is information security regularly reviewed by an independent auditor?
A.18.2.2 | Do the managers regularly review if the security policies and procedures are performed properly in their areas of responsibility?
A.18.2.3 | Are information systems regularly reviewed to check their compliance with the information security policies and standards?
Note on D8: MRC: Insert training records

## ISO27001 clauses (2) (hidden)
Clause | Clause Title | Audit finding | Evidence/Observation
4 | Context of the organization
4.1 | Understanding the organization and its context
4.2 | Understanding the needs and expectations of interested parties
4.3 | Determining the scope of the information security management system
4.4 | Information security management system
5 | Leadership
5.1 | Leadership and Commitment
5.2 | Policy
5.3 | Organization, roles, responsibilities and authorities
6 | Planning
6.1 | Action to address Risk and Opportunities
6.1.1 | General
6.1.2 | Information security risk assessment
6.1.3 | Information security risk treatment
6.2 | Information security objectives and planning to achieve them
7 | Support
7.1 | Resources
7.2 | Competence
7.3 | Awareness
7.4 | Communication
7.5 | Documented information
7.5.1 | General
7.5.2 | Creating & updating
7.5.3 | Control of documented information
8 | Operation
8.1 | Operational planning & control
8.2 | Information security risk assessment
8.3 | Information security risk treatment
9 | Performance evaluation
9.1 | Monitoring, measurement, analysis and evaluation
9.2 | Internal audit
9.3 | Management review
10 | Improvement
10.1 | Nonconfirminty & corrective action
10.2 | Continual improvement
A.5 | Information security policies
A.5.1 | Management direction for information security
A.5.1.1 | Policies for information security
A.5.1.2 | Review of the policies for information security
A.6 | Organization of information security
A.6.1 | Internal organization
A.6.1.1 | Information security roles and responsibilities
A.6.1.2 | Segregation of duties
A.6.1.3 | Contact with authorities
A.6.1.4 | Contact with special interest groups
A.6.1.5 | Information security in project management
A.6.2 | Mobile devices and teleworking
A.6.2.1 | Mobile device policy
A.6.2.2 | Teleworking
A.7 | Human resource security
A.7.1 | Prior to employment
A.7.1.1 | Screening
A.7.1.2 | Terms and conditions of employment
A.7.2 | During employment
A.7.2.1 | Management responsibilities
A.7.2.2 | Information security awareness, education and training
A.7.2.3 | Disciplinary process
A.7.3 | Termination and change of employment
A.7.3.1 | Termination or change of employment responsibilities
A.8 | Asset management
A.8.1 | Responsibility for assets
A.8.1.1 | Inventory of assets
A.8.1.2 | Ownership of assets
A.8.1.3 | Acceptable use of assets
A.8.1.4 | Return of assets
A.8.2 | Information classification
A.8.2.1 | Classification of information
A.8.2.2 | Labeling of information
A.8.2.3 | Handling of assets
A.8.3 | Media handling
A.8.3.1 | Management of removable media
A.8.3.2 | Disposal of media
A.8.3.3 | Physical media transfer
A.9 | Access control
A.9.1 | Business requirements of access control
A.9.1.1 | Access control policy
A.9.1.2 | Access to networks and network services
A.9.2 | User access management
A.9.2.1 | User registration and de-registration
A.9.2.2 | User access provisioning
A.9.2.3 | Management of privileged access rights
A.9.2.4 | Management of secret authentication information of users
A.9.2.5 | Review of user access rights
A.9.2.6 | Removal or adjustment of access rights
A.9.3 | User responsibilities
A.9.3.1 | Use of secret authentication information
A.9.4 | System and application access control
A.9.4.1 | Information access restriction
A.9.4.2 | Secure log-on procedures
A.9.4.3 | Password management system
A.9.4.4 | Use of privileged utility programs
A.9.4.5 | Access control to program source code
A.10 | Cryptography
A.10.1 | Cryptographic controls
A.10.1.1 | Policy on the use of cryptographic controls
A.10.1.2 | Key management
A.11 | Physical and environmental security
A.11.1 | Secure areas
A.11.1.1 | Physical security perimeter
A.11.1.2 | Physical entry controls
A.11.1.3 | Securing offices, rooms and facilities
A.11.1.4 | Protecting against external and environmental threats
A.11.1.5 | Working in secure areas
A.11.1.6 | Delivery and loading areas
A.11.2 | Equipment
A.11.2.1 | Equipment siting and protection
A.11.2.2 | Supporting utilities
A.11.2.3 | Cabling security
A.11.2.4 | Equipment maintenance
A.11.2.5 | Removal of assets
A.11.2.6 | Security of equipment and assets off-premises
A.11.2.7 | Secure disposal or reuse of equipment
A.11.2.8 | Unattended user equipment
A.11.2.9 | Clear desk and clear screen policy
A.12 | Operations security
A.12.1 | Operational procedures and responsibilities
A.12.1.1 | Documented operating procedures
A.12.1.2 | Change management
A.12.1.3 | Capacity management
A.12.1.4 | Separation of development, testing and operational environments
A.12.2 | Protection from malware
A.12.2.1 | Controls against malware
A.12.3 | Backup
A.12.3.1 | Information backup
A.12.4 | Logging and monitoring
A.12.4.1 | Event logging
A.12.4.2 | Protection of log information
A.12.4.3 | Administrator and operator logs
A.12.4.4 | Clock synchronization
A.12.5 | Control of operational software
A.12.5.1 | Installation of software on operational systems
A.12.6 | Technical vulnerability management
A.12.6.1 | Management of technical vulnerabilities
A.12.6.2 | Restrictions on software installation
A.12.7 | Information systems audit considerations
A.12.7.1 | Information systems audit controls
A.13 | Communications security
A.13.1 | Network security management
A.13.1.1 | Network controls
A.13.1.2 | Security of network services
A.13.1.3 | Segregation in networks
A.13.2 | Information transfer
A.13.2.1 | Information transfer policies and procedures
A.13.2.2 | Agreements on information transfer
A.13.2.3 | Electronic messaging
A.13.2.4 | Confidentiality or nondisclosure agreements
A.14 | System acquisition, development and maintenance
A.14.1 | Security requirements of information systems
A.14.1.1 | Information security requirements analysis and specification
A.14.1.2 | Securing application services on public networks
A.14.1.3 | Protecting application services transactions
A.14.2 | Security in development and support processes
A.14.2.1 | Secure development policy
A.14.2.2 | System change control procedures
A.14.2.3 | Technical review of applications after operating platform changes
A.14.2.4 | Restrictions on changes to software packages
A.14.2.5 | Secure system engineering principles
A.14.2.6 | Secure development environment
A.14.2.7 | Outsourced development
A.14.2.8 | System security testing
A.14.2.9 | System acceptance testing
A.14.3 | Test data
A.14.3.1 | Protection of test data
A.15 | Supplier relationships
A.15.1 | Information security in supplier relationships
A.15.1.1 | Information security policy for supplier relationships
A.15.1.2 | Addressing security within supplier agreements
A.15.1.3 | Information and communication technology supply chain
A.15.2 | Supplier service delivery management
A.15.2.1 | Monitoring and review of supplier services
A.15.2.2 | Managing changes to supplier services
A.16 | Information security incident management
A.16.1 | Management of information security incidents and improvements
A.16.1.1 | Responsibilities and procedures
A.16.1.2 | Reporting information security events
A.16.1.3 | Reporting information security weaknesses
A.16.1.4 | Assessment of and decision on information security events security incidents
A.16.1.5 | Response to information security incidents
A.16.1.6 | Response to information security incidents
A.16.1.7 | Response to information security incidents
A.17 | Information security aspects of business continuity management
A.17.1 | Information security continuity
A.17.1.1 | Planning information security continuity
A.17.1.2 | Implementing information security continuity
A.17.1.3 | Verify, review and evaluate information security continuity
A.17.2 | Redundancies
A.17.2.1 | Availability of information processing facilities
A.18 | Compliance
A.18.1 | Compliance with legal and contractual requirements
A.18.1.1 | Identification of applicable legislation and contractual requirements
A.18.1.2 | Intellectual property rights
A.18.1.3 | Protection of records
A.18.1.4 | Privacy and protection of personally identifiable information
A.18.1.5 | Regulation of cryptographic controls
A.18.2 | Information security reviews
A.18.2.1 | Independent review of information security
A.18.2.2 | Compliance with security policies and standards
A.18.2.3 | Technical compliance review

## 27K-IA (arc) (hidden)
Clause | Requirement of the standard | Comply (Yes/No) | Evidence
4.2 | Did the organization determine interested parties? | Yes | Client discussions and site assessment visits; signed quotations; processes for printing and fulfilment communicated to clients
4.2 | Does the list of all of interested parties’ requirements exist? | Yes | For clients specifying the requirements, these are documented through email correspondences
4.3 | Is the scope documented with clearly defined boundaries and interfaces? | Yes | ISMS applies specially to the digital printing production and mail insertion (or fulfilment) processes
5.1 | Are the general ISMS objectives compatible with the strategic direction? | Yes | The key ISMS objective is to protect confidentiality, integrity and availability of data for the digital printing and fulfilment areas
5.1 | Does management ensure that ISMS achieves its objectives? | Yes | Management has allocated the resources, implement specific job roles, responsibilities and accountabilities; with the supporting ISMS processes to enforce the objectives; the management review meeting was conducted to affirm Management's commitment and leadership
5.2 | Does Information Security Policy exist with objectives or framework for setting objectives? | Yes | ISMS policy statement and manual (ISMS-01) states the objectives and describes the framework for setting and reviewing the objectives
5.2 | Is Information Security Policy communicated within the company? | Yes | HODs and managers conducted briefing and training sessions to communicate the IS policy and objectives to the employees from the digital printing production and fulfilment, customer service and sales departments and functions - refer to the training records
5.3 | Are roles and responsibilities for information security assigned and communicated? | Yes | Roles and responsibilities for IS is defined and assigned in the IS policy manual (ISMS-01); which is communicated to management; management has communicated this to the employees
6.1.2 | Is the risk assessment process documented, including the risk acceptance criteria and criteria for risk assessment? | Yes | The risk assessment (RA) process is documented in the "Risk Assessment and Treatment Methodology" manual (ISMS-03); including the RA and acceptance criteria
6.1.2, 8.2 | Are the risks identified, their owners, likelihood, consequences, and the level of risk; are these results documented? | Yes | The risk assessment (RA) evaluation has been documented in the RA template; results are documented in the RA report (Appendix 3 of ISMS-03)
6.1.3 | Is the risk treatment process documented, including the risk treatment options? | Yes | Current controls are adequate; no additional risk treatment is required; a risk treatment plan (RTP) template is available
6.1.3, 8.3 | Are all the unacceptable risks treated using the options and controls from Annex A; are these results documented? | Yes | Existing risk controls (Annex A) pertaining to policies, processes and procedures are adequate; which are documented in the RA template
6.1.3 | Is Statement of Applicability produced with justifications and status for each control? | Yes | The applicable controls and justifications are listed in the Statement of Applicability document (ISMS-02)
6.1.3, 8.3 | Does Risk treatment plan exist, approved by risk owners? | Yes | A risk treatment plan table is available; current risk controls are adequate
6.2 | Does Risk treatment plan define who is responsible for implementation of which control, with which resources, what are the deadlines, and what is the evaluation method? | NA | Current controls are adequate; no additional risk treatment is required; a risk treatment plan (RTP) template is available
7.1 | Are adequate resources provided for all the elements of ISMS? | Yes | Management has been involved in the ISMS; SMBD, IT Administrator and Digital Printing Manager were intensively involved in setting up the relevant policies, procedures and methodology, and the implementation - documented ISMS activities, findings and report
7.2 | Are required competences defined, trainings performed, and records of competences maintained? | Yes | ISMS competencies are defined in the job descriptions; training records maintained documents the relevant training conducted
7.3 | Is the personnel aware of Information security policy, of their role, and consequences of not complying with the rules? | Yes | Employees within the ISMS scope a briefed on the IS policies and supporting policies and procedures; potential disciplinary actions for acts that are non-compliant to the ISMS requirements - will be meted out in accordance to Ministry of Manpower regulatory requirements
7.4 | Does the process for communication related to information security exist, including the responsibilities and what to communicate? | Yes | The policy statement and the ISMS requirements are communicated to the employees - as is documented in the training record
7.5 | Does the process for managing documents and records exist, including who reviews and approves documents, where and how they are published, stored and protected? | Yes | A master records management table is maintained under the "Procedures for Document and Record Control" (ISMS-04); each individual policy and procedure manual contains records for the maintenance of the contents for each of the documents
7.5 | Are documents of external origin controlled? | Yes | Relevant records of external origin are documented in the master records management table; the relevant documents will be marked "CONFIDENTIAL"
8.1 | Are outsourced processes identified and controlled? | Yes | The "Supplier Security Policy" (ISMS-11) is supported by the relevant procedures like the "Data Handling" (ISMS-18) manual
9.1 | Is it defined what needs to be measured, by which method, who is responsible, who will analyse and evaluate the results? | Yes | Objectives are defined on several key criteria and targets: change management, user management access, IT infrastructure security, no. of security incidents, internal audits, IT support
9.1 | Are the results of measurement documented and reported to responsible persons? | Yes | Results will be measured and documented; reported to the Management
9.2 | Does an audit program exist that defines the timing, responsibilities, reporting, audit criteria and scope? | Yes | The procedure for internal audit is documented (ISMS-06); audit records and report are maintained
9.2 | Are internal audits performed according to audit program, results reported through the Internal audit report and relevant corrective actions raised? | Yes | According to internal audit procedures (ISMS-06); internal audit report is presented to Management; approved improvements and corrective actions are tracked in the corrective actions forms
9.3 | Is management review regularly performed, and are the results documented in minutes of the meeting? | Yes | Management review meetings are carried out every 6 months; minutes recorded includes the areas reviewed and the outcome
9.3 | Did management decide on all the crucial issues important for the success of the ISMS? | Yes | Decisions made during the Management review meeting
10.1 | Does the organization react to every nonconformity? | Yes | Management approved corrective actions are implemented
10.1 | Does the organization consider eliminating the cause of nonconformity and, where appropriate, take corrective action? | Yes | Management approved corrective actions are implemented
10.1 | Are all nonconformities recorded, together with corrective actions? | Yes | Management approved corrective actions are recorded in the corrective actions form
A.5.1.1 | Are all necessary information security policies approved by management and published? | Yes | All relevant ISMS policy and procedure manuals are approved by SMBD (Management appointed representative) and published (electronically)
A.5.1.2 | Are all information security policies reviewed and updated? | Yes | All relevant ISMS policy and procedure manuals will be reviewed every 6 months, and will be approved by SMBD (Management appointed representative) and published (electronically)
A.6.1.1 | Are all information security responsibilities clearly defined through one or several documents? | Yes | The ISMS policy (ISMS-01) and job descriptions (JDs) defines the roles, responsibilities and accountabilities; supplementary policy and procedure manuals supporting specify details of the tasks and activities for each role
A.6.1.2 | Are duties and responsibilities defined in such a way to avoid conflict of interest, particularly with the information and systems where high risks are involved? | Yes | The ISMS policy (ISMS-01) and JDs segregate the roles and responsibilities to avoid conflicts
A.6.1.3 | Is it clearly defined who should be in contact with which authorities? | Yes | The persons responsible to be in contact with authorities are defined in the JDs
A.6.1.4 | Is it clearly defined who should be in contact with special interest groups or professional associations? | Yes | The IT Administrator will be tasked to be in contact with special interest groups and professional associations - as documented in the JD
A.6.1.5 | Are information security rules included in every project? | Yes | Every digital printing job will comply with the information security rules - refer data handling (ISMS-18) and digital printing process and job flow (ISMS-19)
A.6.2.1 | Are there rules for secure handling of mobile devices? | Yes | Secure use of mobile devices is specified in the ISMS policy (ISMS-01)
A.6.2.2 | Are there rules defining how the company information is protected at teleworking sites? | Yes | Control of information when teleworking is specified in the ISMS policy (ISMS-01)
A.7.1.1 | Are background checks performed on candidates for employment or for contractors? | NA | Company will conduct reference checks on potential new employees; detail background checks and screening is NOT carried out so as to comply with Gov regulatory requirements
A.7.1.2 | Do the agreements with employees and contractors specify the information security responsibilities? | Yes | Agreement with employees are documented in the signed asset and confidential statement agreement; contractors' agreements will contain terms on maintaining information confidentiality
A.7.2.1 | Is management actively requiring all employees and contractors to comply with information security rules? | Yes | Management regularly supervises employees and contractors - refer to documented manuals for "Procedures for Working in Secure Areas", "Security of the Digital Dept Operations Area", "Desktop PC Security", "Data Handling" and "Digital Printing Process and Job Flow"
A.7.2.2 | Are all relevant employees and contractors being trained to perform their security duties, and do the awareness programs exist? | Yes | Employees are briefed on policies(ISMS-01 and supplementary policies) and manuals (as listed above) - at least once every 6 months
A.7.2.3 | Have all employees who have committed a security breach been subject to a formal disciplinary process? | NA | Currently no security breach has occurred
A.7.3.1 | Are information security responsibilities that remain valid after the termination of employment defined in the agreement? | Yes | The Asset and Confidentiality Statement signed by employees includes a clause specifying that IS responsibilities for the employee remain valid after termination
A.8.1.1 | Is an Inventory of assets drawn up? | Yes | The assets inventory list is maintained
A.8.1.2 | Does every asset in Inventory of assets have a designated owner? | Yes | Each asset has an assigned owner; the asset owner is required to sign the asset and confidentiality statement agreement
A.8.1.3 | Are the rules for appropriate handling of information and assets documented? | Yes | The ISMS policy (ISMS-01) is supplemented by relevant policies and procedure manuals - like the "Operating Procedures for Information and Communication Technology" (ISMS-08), "Clear Desk and Clear Screen Policy" (ISMS-13), "Procedures for Working in Secure Areas" (ISMS-16) and "Data Handling" (ISMS-18)
A.8.1.4 | Did all the employees and contractors return all the company assets when their employment was terminated? | Yes | The requirements in the ISMS policy (ISMS-01) and asset and confidentiality agreement are carried upon termination
A.8.2.1 | Is the information classified according to specified criteria? | Yes | Information classification is specified as "CONFIDENTIAL", "INTERNAL" and "PUBLIC"
A.8.2.2 | Is the classified information labelled according to the defined procedures? | Yes | Information are labelled according the classifications above; any document that is not labelled is classified as "INTERNAL"
A.8.2.3 | Are there procedures which define how to handle classified information? | Yes | Procedures for information classification is listed in ISMS policy (ISMS-01); this is communicated to the employees
A.8.3.1 | Are there the procedures which define how to handle removable media in line with the classification rules? | Yes | The ISMS policy (ISMS-01) document specifies the handling of removable media
A.8.3.2 | Are there formal procedures for disposing of the media? | Yes | The ISMS (ISMS-01) and Disposal and Destruction (ISMS-14) Policies specifies the method for disposal of media
A.8.3.3 | Is the media that contains sensitive information protected during transportation? | Yes | Information that are transported or transmitted are controlled according to the specifications in the ISMS Policy (ISMS-01) and Policy on the Use of Cryptographic Controls (ISMS-12)
A.9.1.1 | Is there an Access control policy which defines business and security requirements for access control? | Yes | The ISMS Policy (ISMS-01) specifies the access control policies
A.9.1.2 | Do the users have access only to those networks and services they are specifically authorized for? | Yes | The ISMS Policy (ISMS-01) specifies the access and network control policies
A.9.2.1 | Are access rights provided via a formal registration process? | Yes | The ISMS Policy (ISMS-01) specifies requirements for access rights approval and registration
A.9.2.2 | Is there a formal access control system when logging into information systems? | Yes | The control is implemented based on standard operating and application systems access rights controls
A.9.2.3 | Are privileged access rights managed with special care? | Yes | Access rights are managed according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.9.2.4 | Are initial passwords and other secret authentication information provided in a secure way? | Yes | Access rights are managed according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.9.2.5 | Do asset owners periodically check all the privileged access rights? | NA | This check is carried out by the IT Administrator
A.9.2.6 | Have the access rights to all employees and contractors been removed upon the termination of their contracts? | Yes | Access rights are removed n accordance to the ISMS Policy (ISMS-01)
A.9.3.1 | Are there clear rules for users on how to protect passwords and other authentication information? | Yes | Access rights are managed according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.9.4.1 | Is the access to databases and applications restricted according to the Access control policy? | Yes | Access rights are managed according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.9.4.2 | Is secure log-on required on systems according to the Access control policy? | Yes | Control of log-on to systems are managed according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.9.4.3 | Are the systems that manage passwords interactive, and enable the creation of secure passwords? | No | Initial passwords are generated by the IT Administrator
A.9.4.4 | Is the use of utility tools that can override the security controls of applications and systems strictly controlled and limited to narrow circle of employees? | Yes | Control on use of utilities is restricted to the IT Administrator and SMBD (Management representative)
A.9.4.5 | Is the access to source code restricted to authorized persons? | NA | No application development is undertaken
A.10.1.1 | Does the policy that regulates encryption and other cryptographic controls exist? | Yes | The requirements are documented in the ISMS Policy (ISMS-01) and Policy on the Use of Cryptographic Controls (ISMS-12)
A.10.1.2 | Are the cryptographic keys properly protected? | Yes | These are managed by the IT Administrator and SMBD; users are required to follow the Desktop PC Security (ISMS-17) and Data Handling (ISMS-18) procedures
A.11.1.1 | Do secure areas that protect sensitive information exist? | Yes | The requirements are documented in the ISMS Policy (ISMS-01), Procedures for Working in Secure Areas (ISMS-15) and Security of the Digital Dept Operation Area (ISMS-16)
A.11.1.2 | Is the entrance to secure areas protected with controls that allow only the authorized persons to enter? | Yes | Controls and procedures are implemented in accordance to the ISMS Policy (ISMS-01), Procedures for Working in Secure Areas (ISMS-15) and Security of the Digital Dept Operation Area (ISMS-16); CCTVs and the surveillance system are implemented
A.11.1.3 | Are secure areas located in such a way that they are not visible to outsiders, and not easily reached from the outside? | Yes | Controls and procedures are implemented in accordance to the ISMS Policy (ISMS-01), Procedures for Working in Secure Areas (ISMS-15) and Security of the Digital Dept Operation Area (ISMS-16); CCTVs and the surveillance system are implemented
A.11.1.4 | Are the alarms, fire-protection, and other systems installed? | Yes | Fire protection and alarm systems are implemented; requirements comply with the regulations (that is, SCDF and BCA)
A.11.1.5 | Are working procedures for secure areas defined and complied with? | Yes | Controls and procedures are implemented in accordance to the ISMS Policy (ISMS-01), Procedures for Working in Secure Areas (ISMS-15) and Security of the Digital Dept Operation Area (ISMS-16); CCTVs and the surveillance system are implemented
A.11.1.6 | Are delivery and loading areas controlled in such a way that unauthorized persons cannot enter the company premises? | Yes | Controls and procedures for access to the external access areas to the Digital Printing area are implemented in accordance to the ISMS Policy (ISMS-01), Procedures for Working in Secure Areas (ISMS-15) and Security of the Digital Dept Operation Area (ISMS-16); CCTVs and the surveillance system are implemented; loading and unloading activities at the ground floor are supervised by the managers or supervisors
A.11.2.1 | Is the equipment sited in such a way to protect it from unauthorized access, and from environmental threats? | Yes | Equipment assets are placed or stored in the secured office premises; possible damage by environmental threats (e.g. water leakage) are minimize by placing the equipment away from such potential hazard areas
A.11.2.2 | Does the equipment have an uninterruptible power supply? | Yes | Critical equipment is protected by UPS
A.11.2.3 | Are the power and telecommunication cables adequately protected? | Yes | Electrical and telecommunication cable are installed according to industry good practices and local regulatory requirements
A.11.2.4 | Is the equipment maintained regularly according to manufacturers’ specifications and good practice? | Yes | IT equipment are maintained internally by the IT Administrator; printing, air-con, CCTV and access control systems are maintained by the relevant contractors under the supervision of the managers and supervisors in the department
A.11.2.5 | Is the authorization for information and other assets given each time they are taken out of the company premises? | Yes | Information and other assets that are NOT issued to Management requires authorization before removal from the company's premises; Management are issued notebook PCs that are pre-authorized for removal
A.11.2.6 | Are the company assets adequately protected when they are not located at the company premises? | Yes | Company assets will be protected by the persons authorized to remove the item from the company's premises
A.11.2.7 | Are all the information and licensed software removed from media or equipment containing media when disposed of? | Yes | Access rights are managed according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.11.2.8 | Are users protecting their equipment when not in physical possession of it? | Yes | Users are requirement to manage their assets according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.11.2.9 | Is there a policy which forces users to remove papers and media when not present, and lock their screens? | Yes | Employees are required to follow the Clear Desk and Clear Screen Policy (ISMS-13)
A.12.1.1 | Have the operating procedures for IT processes been documented? | Yes | The procedures are documented in the Operating Procedures for Information and Communication Technology (ISMS-08)
A.12.1.2 | Are all the changes to IT systems, but also to other processes that could affect information security, strictly controlled? | Yes | The procedures are documented in the Procedures for Document and Record Control (ISMS-04)
A.12.1.3 | Does someone monitor use of resources and project the required capacity? | Yes | This is monitored according to the Data Handling (ISMS-18) and Digital Printing Process and Job Flow (ISMS-19) manuals
A.12.1.4 | Are development, testing and production environments strictly separated? | Yes | No application development is undertaken; new software and hardware are tested in a controlled environment
A.12.2.1 | Are anti-virus software, and other software for malware protection, installed and updated? | Yes | The procedures are documented in the Operating Procedures for Information and Communication Technology (ISMS-08)
A.12.3.1 | Is the backup policy developed; is the backup performed according to this policy? | Yes | The back up policy is documented in the ISMS Policy (ISMS-01); the IT Administrator maintains a backup log
A.12.4.1 | Are all user logs, faults and other events from IT systems logged, and does someone check them? | Yes | Any information security incidents will be logged according to the incident log table in accordance to the Incident Management Procedure (ISMS-07)
A.12.4.2 | Are logs protected in such a way that unauthorized persons cannot change them? | Yes | Access to the logs will be restricted to the IT Administrator and SMBD
A.12.4.3 | Are administrator logs protected in such a way that system administrators cannot change them or delete them; are they regularly checked? | NA | This is not a feasible option with respect to the organization set up and staffing requirements
A.12.4.4 | Are clocks on all IT systems synchronized with a single source of correct time? | Yes | Clock synchronization is standardized
A.12.5.1 | Is installation of software strictly controlled; do procedures exist for that purpose? | Yes | Installation of software is controlled strictly by the IT Administrator upon the approval from the SMBD
A.12.6.1 | Is there someone in charge of collecting information about vulnerabilities, and are those vulnerabilities promptly resolved? | Yes | The IT Administrator is responsible
A.12.6.2 | Are there specific rules that define restrictions of software installation by users? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.12.7.1 | Are audits of production systems planned and executed in such a way that they minimize the risk of disruption? | Yes | The internal audit process is carried out at least once every 6 months
A.13.1.1 | Are the networks controlled in such a way that they protect information in systems and applications? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.13.1.2 | Are security requirements for in-house and external network services defined, and included in agreements? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.13.1.3 | Are groups of users, services and systems segregated in different networks? | No | The organization is very small and it is not feasible to segregate users and placed them on different networks
A.13.2.1 | Is the protection of information transfer regulated in formal policies and procedures? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.13.2.2 | Do agreements with third parties exist which regulate the security of information transfer? | NA | The current business needs do not require the company to have agreements with third parties to regulate the security of information transfer
A.13.2.3 | Are the messages that are exchanged over the networks properly protected? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.13.2.4 | Did the company list all the confidentiality clauses that need to be included in agreements with third parties? | NA | Current business process is based on ad hoc projects; which do not require confidential term agreements to be executed
A.14.1.1 | Are security requirements defined for new information systems, or for any changes to them? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.14.1.2 | Is the information involved in applications that is transferred through the public networks appropriately protected? | NA | No application information is transmitted through public networks
A.14.1.3 | Is the information involved in transactions that is transferred through the public networks appropriately protected? | Yes | Information received and sent to clients are encrypted or password protected whenever possible
A.14.2.1 | Are the rules for the secure development of software and systems defined? | NA | No software development is required
A.14.2.2 | Do formal change control procedures exist for making any changes to the new or existing systems? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.14.2.3 | Are critical applications tested after the operating systems have been changed or updated? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.14.2.4 | Are only the changes that are really necessary performed to information systems? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.14.2.5 | Are the principles for engineering secure systems documented and implemented? | Yes | Any new systems will be documented during implementation, whenever appropriate
A.14.2.6 | Is the development environment appropriately secured from unauthorized access and change? | NA | No software development is required
A.14.2.7 | Is the outsourced development of systems monitored? | NA | No software development is required
A.14.2.8 | Is testing for proper implementation of security requirements performed during the development? | Yes | The Secure Development Policy (ISMS-10) specifies the controls for the implementation of new software and hardware
A.14.2.9 | Are the criteria for accepting the systems defined? | Yes | The Secure Development Policy (ISMS-10) specifies the controls for the implementation of new software and hardware
A.14.3.1 | Are the test data carefully selected and protected? | Yes | The Secure Development Policy (ISMS-10) specifies the controls for the implementation of new software and hardware
A.15.1.1 | Is the policy on how to treat the risks related to suppliers and partners documented? | Yes | The ISMS Policy (ISMS-01) and the risk assessment methodology; documented in the risk assessment template
A.15.1.2 | Are all the relevant security requirements included in the agreements with the suppliers and partners? | NA | Only agreement signed with SingTel - based on their standard agreement; no agreement is enforced for other suppliers and partners
A.15.1.3 | Do the agreements with cloud providers and other suppliers include security requirements for ensuring the reliable delivery of services? | Yes | The main cloud service provider is the email services - based on a standard agreement issued by the service provider
A.15.2.1 | Are suppliers regularly monitored for compliance with the security requirements, and audited if appropriate? | Yes | Suppliers providing service and support at the printing department area will be supervised and monitored
A.15.2.2 | When making changes to arrangements and contracts with suppliers and partners, are risks and existing processes taken into account? | Yes | The risk assessment template documents the risks
A.16.1.1 | Are procedures and responsibilities for managing incidents clearly defined? | Yes | This is specified in the Incident Management Procedure (ISMS-07); captured in the incident log template, if appropriate
A.16.1.2 | Are all information security events reported in a timely manner? | NA | No major incidents occurred since implementation
A.16.1.3 | Are employees and contractors reporting on security weaknesses? | Yes | This will be documented during the risk assessment
A.16.1.4 | Are all security events assessed and classified? | NA | No major incidents occurred since implementation
A.16.1.5 | Are procedures on how to respond to incidents documented? | Yes | This is specified in the Incident Management Procedure (ISMS-07); captured in the incident log template, if appropriate
A.16.1.6 | Are security incidents analysed in order to gain knowledge on how to prevent them? | Yes | This is specified in the Incident Management Procedure (ISMS-07)
A.16.1.7 | Do procedures exist which define how to collect evidence that will be acceptable during the legal process? | Yes | This is specified in the Incident Management Procedure (ISMS-07)
A.17.1.1 | Are requirements for continuity of information security defined? | Yes | Continuity of information requirements are specified in the ISMS Policy (ISMS-01)
A.17.1.2 | Do procedures exist that ensure the continuity of information security during a crisis or a disaster? | Yes | Procedures are documented in the Business Continuity Plan (BCP-01)
A.17.1.3 | Is exercising and testing performed in order to ensure effective response? | No | Testing is limited to recovering back up date; mobilisation and relocation test at the BCP alternate site is to be carried out
A.17.2.1 | Does IT infrastructure have redundancy (e.g. secondary location) to fulfil the expectations during disasters? | Yes | Procedures are documented in the Business Continuity Plan (BCP-01)
A.18.1.1 | Are all legislative, regulatory, contractual and other security requirements listed and documented? | Yes | The Procedures for Identification of Requirements (ISMS-05) specifies the procedures; the corresponding appendix documents the security requirements
A.18.1.2 | Do procedures exist that ensure the enforcement of intellectual property rights, in particular, the used of licensed software? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.18.1.3 | Are all the records protected according to identified regulatory, contractual and other requirements? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01) and Operating Procedures for Information and Communication Technology (ISMS-08)
A.18.1.4 | Is personally identifiable information protected as required in laws and regulations? | Yes | Specific rules in this area are enforced according to the ISMS Policy (ISMS-01)
A.18.1.5 | Are cryptographic controls used as required in laws and regulations? | No | Currently, there are no local regulations applicable
A.18.2.1 | Is information security regularly reviewed by an independent auditor? | Yes | Internal audit will be carried out by an external party
A.18.2.2 | Do the managers regularly review if the security policies and procedures are performed properly in their areas of responsibility? | Yes | Management will review this during the Management Review Meeting which will be carried out at least once every 6 months
A.18.2.3 | Are information systems regularly reviewed to check their compliance with the information security policies and standards? | Yes | The IT and internal audit will be carried out at least once every 6 months
Note on D8: MRC: Insert training records